## general_report
Issue Type | Assignee | Key | Summary | Reporter | Priority | Status | Resolution | Created | Updated | Due Date | Target Date | Classification | Story Points | Labels | Epic Link | Component/s | Performance Test | QCOE Test Required | WSOAPIData Story Type
Story | Unassigned | KOSPS-2 | View Product Detail Page | Aruna X Sharma | Medium | To Do | Fixed | 2016-12-06 01:40 | 2017-03-06 19:00 |  | 2017-03-13 | 1 | 2 | PDP, Reviewed-PDM, Reviewed-Team | PDP_EPIC | UI | No | Yes | Functional
Story | Sudhir Ikke | KOSPS-8 | Product Tile: Product Hero Image Zoom | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-07 01:58 | 2017-03-02 12:51 |  | 2017-03-13 | 0 | 2 | PDP, Reviewed-PDM, Reviewed-Team | Product Tile | UI | No | Yes | Functional
Story | Nagendra Mirajkar | KOSPS-9 | UI: Product Title | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-07 02:04 | 2017-02-22 | 2017-02-22 | 2017-02-27 | 0 | 18 | PDP, Reviewed-PDM, Reviewed-Team | PDP - Static Initial Page | UI | No | Yes | Functional
Story | Nagendra Mirajkar | KOSPS-10 | Product Tile: Viewing Swatches | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-07 02:30 | 2017-03-01 20:15 | 2017-02-22 | 2017-03-13 | 0 | 21 | PDP, Reviewed-PDM, Reviewed-Team | PDP - Static Initial Page | UI | No | Yes | Functional
Story | Sudhir Ikke | KOSPS-11 | PDP Redesign: Quantity | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-07 02:31 | 2017-03-01 20:16 | 2017-02-24 | 2017-03-13 | 0 | 21 | PDP, Reviewed-PDM, Reviewed-Team | PDP - Static Initial Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-12 | PDP Redesign: Max Quantity | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-07 02:33 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 18 | PDP, Reviewed-PDM, Reviewed-Team | Product Tile | UI | No | Yes | Functional
Story | Unassigned | KOSPS-13 | PDP Redesign: Add To Bag | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-07 02:34 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 21 | PDP, Reviewed-PDM, Reviewed-Team | Product Tile | UI | No | Yes | Functional
Story | Sudhir Ikke | KOSPS-14 | PDP Redesign: Size & Fit Anchor | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-07 02:35 | 2017-03-01 20:28 | 2017-02-23 | 2017-03-13 | 0 | 21 | PDP, Reviewed-PDM, Reviewed-Team | PDP - Static Initial Page | UI | No | Yes | Functional
Story | Sudhir Ikke | KOSPS-15 | PDP Redesign: View Larger | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-07 02:36 | 2017-03-02 12:55 |  | 2017-03-13 | 0 | 13 | PDP, Reviewed-PDM, Reviewed-Team | Product Tile | UI | No | Yes | Functional
Story | Sudhir Ikke | KOSPS-16 | Product Tile : Hero Image | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-07 02:40 | 2017-03-01 20:29 | 2017-02-22 | 2017-03-13 | 0 | 13 | PDP, Reviewed-PDM, Reviewed-Team | PDP - Static Initial Page | UI | No | Yes | Functional
Story | Sudhir Ikke | KOSPS-17 | Product Tile: Video | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-07 02:42 | 2017-03-01 20:30 | 2017-02-23 | 2017-03-13 | 0 | 18 | PDP, Reviewed-PDM, Reviewed-Team | PDP - Static Initial Page | UI | No | Yes | Functional
Story | Sudhir Ikke | KOSPS-18 | Product Tile: Alternate Image | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-07 02:43 | 2017-03-01 20:30 | 2017-02-22 | 2017-03-13 | 0 | 13 | PDP, Reviewed-PDM, Reviewed-Team | PDP - Static Initial Page | UI | No | Yes | Functional
Story | Vikram Mhatre | KOSPS-19 | Product Tile: Product Detail Badges | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-07 02:44 | 2017-03-01 20:30 | 2017-02-24 | 2017-03-13 | 0 | 21 | PDP, Reviewed-PDM, Reviewed-Team | PDP - Static Initial Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-21 | Inventory check before PDP page load | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-07 02:50 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PDP, Reviewed-PDM | PDP_EPIC | UI | No | Yes | Functional
Story | Unassigned | KOSPS-22 | Error Messaging Box | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-07 02:52 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PDP, Reviewed-PDM, Reviewed-Team | PDP_EPIC | UI | No | Yes | Functional
Story | Unassigned | KOSPS-23 | Back button logic | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-07 02:53 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 8 | PDP, Reviewed-PDM | PDP_EPIC | UI | No | Yes | Functional
Story | Unassigned | KOSPS-24 | Show Spinner on click of Add to Bag as system is working | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-07 02:58 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 8 | PDP, Reviewed-PDM, Reviewed-Team | PDP_EPIC | UI | No | Yes | Functional
Story | Nagendra Mirajkar | KOSPS-26 | Pricing: Not discounted/Simple Price for simple and Product with variants | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-07 03:03 | 2017-03-01 20:31 | 2017-02-24 | 2017-03-13 | 0 | 21 | PDP, Reviewed-PDM | PDP - Static Initial Page | UI | No | Yes | Functional
Story | Udeyandra Kumar | KOSPS-27 | Pricing: Discounted Price | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-07 03:05 | 2017-03-03 13:22 |  | 2017-03-13 | 0 | 18 | PDP, Reviewed-PDM | PDP_PRICING | UI | No | Yes | Functional
Story | Shubhendu Singh | KOSPS-28 | Pricing: Suppressed Price | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-07 03:06 | 2017-03-03 13:17 |  | 2017-03-13 | 0 | 13 | PDP, Reviewed-PDM | PDP_PRICING | UI | No | Yes | Functional
Story | Shubhendu Singh | KOSPS-29 | Pricing: Tiered Pricing | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-07 03:07 | 2017-03-03 13:24 |  | 2017-03-13 | 0 | 13 | PDP, Reviewed-PDM | PDP_PRICING | UI | No | Yes | Functional
Story | Shubhendu Singh | KOSPS-30 | Suppressed Pricing Message | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-07 03:08 | 2017-03-03 13:11 |  | 2017-03-13 | 0 | 18 | PDP, Reviewed-PDM, Reviewed-Team | PDP_PRICING | UI | No | Yes | Functional
Story | Sudhir Ikke | KOSPS-42 | Store Pick Up Tab - PDP | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-07 04:39 | 2017-03-01 20:31 | 2017-02-24 | 2017-03-13 | 0 | 21 | Reviewed-PDM, Reviewed-Team | PDP - Static Initial Page | UI | No | Yes | Functional
Story | Tarun Agarwal | KOSPS-43 | Find In Store - PDP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-07 04:41 | 2017-03-03 13:27 |  | 2017-03-13 | 0 | 18 | PDP, Reviewed-PDM, Reviewed-Team | BOPUS_PDP | UI | No | Yes | Functional
Story | Tarun Agarwal | KOSPS-44 | BOPUS - Kill Switch | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-07 04:43 | 2017-02-27 16:18 |  | 2017-02-27 | 0 | 8 | Reviewed-PDM, Reviewed-Team | PDP - Static Initial Page | UI | No | Yes | Functional
Story | Tarun Agarwal | KOSPS-45 | User clicks on Store Pick UP Tab - PDP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-07 04:47 | 2017-02-16 14:26 |  | 2017-02-27 | 0 | 21 | PDP, Reviewed-PDM, Reviewed-Team | BOPUS_PDP | UI | No | Yes | Functional
Story | Tarun Agarwal | KOSPS-46 | Error Messages BOPUS - PDP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-07 05:12 | 2017-02-16 14:25 |  | 2017-02-27 | 0 | 21 | Reviewed-PDM, Reviewed-Team | BOPUS_PDP | UI | No | Yes | Functional
Story | Unassigned | KOSPS-49 | Omniture Tracking - Alternative Images - PDP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-07 11:23 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PDP, Reviewed-PDM | Omniture_PDP | UI | No | Yes | Functional
Story | Unassigned | KOSPS-50 | Omniture tracking - PDP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-07 11:27 | 2017-03-06 19:01 |  | 2017-03-13 | 0 | 2 | PDP, Reviewed-PDM | Omniture_PDP | UI | No | Yes | Functional
Story | Unassigned | KOSPS-51 | Omniture tracking of Video views - PDP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-07 11:30 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PDP, Reviewed-PDM | Omniture_PDP | UI | No | Yes | Functional
Story | Shubhendu Singh | KOSPS-54 | Group Pricing - PDP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-09 06:11 | 2017-03-03 13:19 |  | 2017-03-13 | 0 | 13 | PDP, Reviewed-PDM | PDP_PRICING | UI | No | Yes | Functional
Story | Geetanjali Mandarapu | KOSPS-60 | Instance level debugging | Manan Shah | High | In Progress | Unresolved | 2016-12-09 15:53 | 2017-02-27 08:34 |  | 2017-02-27 | 0 | 13 |  | PE SnB |  | No | Yes | Technical
Story | Unassigned | KOSPS-61 | GWP - Buy X$ worth of product and get Gift - PDP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-11 23:21 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PDP, Reviewed-PDM | Promotions_PDP | UI | No | Yes | Functional
Story | Unassigned | KOSPS-62 | GWP - Buy X number of products and get Gift - PDP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-11 23:36 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PDP, Reviewed-PDM | Promotions_PDP | UI | No | Yes | Functional
Story | Unassigned | KOSPS-63 | GWP - Buy X and Get Gift Y - PDP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-12 00:11 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PDP, Reviewed-PDM | Promotions_PDP | UI | No | Yes | Functional
Story | Unassigned | KOSPS-64 | PWP - Buy X# of Product A, Buy Product B for $X - PDP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-12 00:28 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PDP, Reviewed-PDM | Promotions_PDP | UI | No | Yes | Functional
Story | Unassigned | KOSPS-65 | PWP - Buy $ X of Product A, Buy Product B for $X - PDP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-12 01:36 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PDP, Reviewed-PDM | Promotions_PDP | UI | No | Yes | Functional
Story | Unassigned | KOSPS-66 | PWP - Buy X, Be Eligible to purchase Y for Z$ amount - PDP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-12 02:06 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PDP, Reviewed-PDM | Promotions_PDP | UI | No | Yes | Functional
Story | Unassigned | KOSPS-67 | PWP/GWP - Teaser Messages - PDP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-12 02:19 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PDP, Reviewed-PDM | Promotions_PDP | UI | No | Yes | Functional
Story | Rajkumar Gundu | KOSPS-93 | Google cloud Inventory Listener /Apache Kafka Consumer | Srinivas Meenavalli | Medium | In Progress | Unresolved | 2016-12-13 08:40 | 2017-03-01 19:14 |  | 2017-03-13 | 0 | 13 |  | Inventory Data flow (kOS platform) |  | Yes | Yes | Technical
Story | Boggala Narayana Reddy | KOSPS-94 | Process Inventory change Message and update Redis Cache for Price Info | Srinivas Meenavalli | Medium | In Progress | Unresolved | 2016-12-13 08:48 | 2017-03-09 04:22 |  | 2017-03-13 | 0 | 13 |  | Inventory Data flow (kOS platform) |  | Yes | Yes | Technical
Story | Sandeep Sirsgi | KOSPS-100 | INCREMENTAL LOAD - Analysis - Capture the BCC changes | Guru Gautam Rao | Medium | Done | Fixed | 2016-12-13 09:53 | 2017-03-06 14:26 |  | 2017-03-13 | 1 | 18 |  | Catalog Feed | Batch | No | No | Technical
Story | Sudhir Ikke | KOSPS-103 | Accordions - PDP | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-14 04:02 | 2017-03-01 20:31 | 2017-02-22 | 2017-03-13 | 0 | 21 | PDP, Reviewed-PDM | PDP - Static Initial Page | UI | No | Yes | Functional
Story | Sudhir Ikke | KOSPS-172 | Back to Top - PDP | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-19 05:46 | 2017-03-02 12:38 | 2017-03-03 | 2017-03-13 | 0 | 13 | Reviewed-PDM, Reviewed-Team | PDP_EPIC | UI | No | Yes | Functional
Story | Unassigned | KOSPS-173 | Add to List - PDP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-19 07:26 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PDP, Reviewed-PDM | PDP_EPIC | UI | No | Yes | Functional
Story | Unassigned | KOSPS-190 | Gift Registry - PDP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-19 12:49 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PDP, Reviewed-PDM | PDP_EPIC | UI | No | Yes | Functional
Story | Unassigned | KOSPS-200 | When editing an item from registry/list overwrite buttons for Add to List/registry - PDP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-19 23:52 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PDP, Reviewed-PDM | PDP_EPIC | UI | No | Yes | Functional
Story | Unassigned | KOSPS-223 | RR - Collections Page - BCC Page level flags | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-20 10:21 | 2017-03-06 19:01 |  | 2017-03-13 | 0 | 2 | Collection, Reviewed-PDM | Collections Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-224 | Collections Page - Product Selection: AJAX for Add to Bag | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-20 10:26 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | Collection, Reviewed-PDM | Collections Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-225 | Collections Page - Product Selection: Add to Bag Error Messaging | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-20 10:29 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | Collection, Reviewed-PDM | Collections Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-226 | Collections - Max Quantity | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-20 10:34 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | Collection, Reviewed-PDM | Collections Page | UI | No | Yes | Functional
Story | Nagendra Mirajkar | KOSPS-228 | Collections Page - Multimedia: Alt Image Content | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-20 10:50 | 2017-03-02 15:17 | 2017-02-22 | 2017-03-13 | 0 | 21 | Reviewed-PDM, collection_page | PDP Collection - Static Initial Page | UI | No | Yes | Functional
Story | Sudhir Ikke | KOSPS-230 | Collections Page - Accordion Content | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-20 11:00 | 2017-03-02 15:18 | 2017-02-22 | 2017-03-13 | 0 | 21 | Reviewed-PDM, collection_page | PDP Collection - Static Initial Page | UI | No | Yes | Functional
Story | Nagendra Mirajkar | KOSPS-233 | Collections Page - Product Title | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-20 11:12 | 2017-03-02 15:18 | 2017-02-24 | 2017-03-13 | 0 | 13 | Reviewed-PDM, collection_page | PDP Collection - Static Initial Page | UI | No | Yes | Functional
Story | Sudhir Ikke | KOSPS-234 | Collections Page - Hero and Alt Images | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-20 11:15 | 2017-03-02 15:18 | 2017-02-22 | 2017-03-13 | 0 | 13 | Reviewed-PDM, collection_page | PDP Collection - Static Initial Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-235 | Product Configuration - PDP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-20 11:17 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | Collection, Reviewed-PDM | Product Tile | UI | No | Yes | Functional
Story | Nagendra Mirajkar | KOSPS-236 | Collections Page - Simple Pricing Scenario | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-20 11:52 | 2017-03-02 15:19 | 2017-02-24 | 2017-03-13 | 0 | 21 | Reviewed-PDM, collection_page | PDP Collection - Static Initial Page | UI | No | Yes | Functional
Story | Nagendra Mirajkar | KOSPS-240 | Collection Page - Product Level Information: Hero and Alt Images | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-21 00:25 | 2017-03-02 15:16 | 2017-02-22 | 2017-03-13 | 0 | 13 | Reviewed-PDM, collection_page | PDP Collection - Static Initial Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-241 | Product Level Information: Product Configuration | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-21 00:37 | 2017-03-06 19:01 |  | 2017-03-13 | 0 | 21 | Collection, Reviewed-PDM | Collections Page |  | No | Yes | Functional
Story | Udeyandra Kumar | KOSPS-242 | Product Level Information- Simple Pricing Scenario | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-21 02:01 | 2017-03-03 12:55 |  | 2017-03-13 | 0 | 13 | Collection, Reviewed-PDM | Collections Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-243 | Product Level Information- Variable SKU Pricing | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-21 02:15 | 2017-03-06 19:01 |  | 2017-03-13 | 0 | 2 | Collection, Reviewed-PDM | Collections Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-261 | Collection Page - Clearance Products | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-21 03:43 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | Collection, Reviewed-PDM | Collections Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-260 | Collection Page - GWP - Buy X and Get Gift Y | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-21 03:43 | 2017-03-06 19:01 |  | 2017-03-13 | 0 | 2 | Collection, Reviewed-PDM | Collections Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-257 | Collection:GWP-Buy X$ worth of product and get Gift | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-21 03:43 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | Collection, Reviewed-PDM | Collections Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-256 | PWP Accordion: Webstore Product Detail Page - Single Buy, Get Single Discount Item-Collection | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-21 03:43 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | Collection, Reviewed-PDM | Collections Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-255 | GWP/PWP: Teaser Messaging-Collection | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-21 03:43 | 2017-03-06 19:01 |  | 2017-03-13 | 0 | 2 | Reviewed-PDM, collection_page | Collections Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-253 | Omniture Tracking - Social Sharing | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-21 03:43 | 2017-03-06 19:01 |  | 2017-03-13 | 0 | 2 | Collection, Reviewed-PDM | Collections Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-252 | Omniture Tracking - Alt Images | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-21 03:43 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | Collection, Reviewed-PDM | Collections Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-251 | Omniture Tracking - Accordion | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-21 03:43 | 2017-03-06 19:01 |  | 2017-03-13 | 0 | 2 | Collection, Reviewed-PDM | Collections Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-250 | Omniture Tracking - Bazaarvoice | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-21 03:43 | 2017-03-06 19:01 |  | 2017-03-13 | 0 | 2 | Collection, Reviewed-PDM | Collections Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-249 | Omniture Tracking - Landing on Page | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-21 03:43 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 3 | Collection, Reviewed-PDM | Collections Page | UI | No | Yes | Functional
Story | Sudhir Ikke | KOSPS-248 | BOPUS on Collections: Display Store Pick Up Tab - Collection | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-21 03:43 | 2017-03-02 15:17 | 2017-02-24 | 2017-03-13 | 0 | 13 | Reviewed-PDM, collection_page | PDP Collection - Static Initial Page | UI | No | Yes | Functional
Story | Shubhendu Singh | KOSPS-246 | Product Level Information: Tiered Pricing | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-21 03:43 | 2017-03-03 12:54 |  | 2017-03-13 | 0 | 13 | Collection, Reviewed-PDM | Collections Page | UI | No | Yes | Functional
Story | Shubhendu Singh | KOSPS-244 | Product Level Information: Group Pricing | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-21 03:43 | 2017-03-03 12:57 |  | 2017-03-13 | 0 | 13 | Collection, Reviewed-PDM | Collections Page | UI | No | Yes | Functional
Story | Udeyandra Kumar | KOSPS-271 | Preview Pricing - PDP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-21 07:23 | 2017-03-03 13:23 |  | 2017-03-13 | 0 | 8 | PDP, Reviewed-PDM | PDP_PRICING | UI | No | Yes | Functional
Story | Bibhuti Patel | KOSPS-272 | ESK088 Batch Job - Performics Feed - Implementation | Guru Gautam Rao | Medium | In Progress | Unresolved | 2016-12-21 08:04 | 2017-03-08 09:49 |  | 2017-03-13 | 0 | 21 |  | SnB Batch Jobs |  | No | No | Technical
Story | Pranav EK | KOSPS-278 | ESK602 Batch job - Skava Feed - Implementation | Guru Gautam Rao | Medium | In Progress | Unresolved | 2016-12-21 08:44 | 2017-03-03 00:25 |  | 2017-03-13 | 0 | 21 |  | SnB Batch Jobs |  | No | No | Technical
Story | Unassigned | KOSPS-300 | View Collections Page | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-23 02:29 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | Collection, Reviewed-PDM | Collections Page | UI | No | Yes | Functional
Story | Amit Kumar Panda | KOSPS-306 | Collection Page - Title | Aruna X Sharma | Medium | Done | Fixed | 2016-12-27 06:03 | 2017-03-02 15:20 | 2017-02-22 | 2017-03-13 | 1 | 8 | Collection, Reviewed-PDM | PDP Collection - Static Initial Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-307 | Collection Page - Find in Store | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-27 07:13 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 8 | Reviewed-PDM, collection_page | Collections Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-308 | Collection Page - User clicks on Store Pick up Tab | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-27 07:15 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | Reviewed-PDM, collection_page | Collections Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-309 | Collection Page - BOPUS errors | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-27 07:17 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | Reviewed-PDM, collection_page | Collections Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-317 | Spotlight - PMP/SRP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-28 06:01 | 2017-03-06 19:00 | 2017-02-23 | 2017-03-13 | 0 | 21 | PMP, Reviewed-PDM |  | UI | No | Yes | Functional
Story | Unassigned | KOSPS-318 | Visual Navigation - PMP/Search | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-28 06:31 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PMP, Reviewed-PDM | Generic Features - PMP/SRP | UI | No | Yes | Functional
Story | Parthiban Natarajan | KOSPS-319 | Product Image - PMP/Search | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-28 07:34 | 2017-03-02 15:22 | 2017-02-23 | 2017-03-13 | 0 | 13 | PMP, Reviewed-PDM | PMP - Static Initial Page | UI | No | Yes | Functional
Story | Karandeep Singh | KOSPS-320 | Regular or Original Price - PMP/Search | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-28 07:43 | 2017-03-02 15:22 | 2017-02-23 | 2017-03-13 | 0 | 21 | PMP, Reviewed-PDM | PMP - Static Initial Page | UI | No | Yes | Functional
Story | Shubhendu Singh | KOSPS-321 | Sale or Clearance Price - PMP/Search Page | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-28 07:53 | 2017-03-02 13:49 |  | 2017-03-13 | 0 | 18 | PMP, Reviewed-PDM | Product Tile - PMP/SRP | UI | No | Yes | Functional
Story | Shubhendu Singh | KOSPS-322 | Suppressed pricing - PMP/Search Page | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-28 08:02 | 2017-03-02 13:51 |  | 2017-03-13 | 0 | 13 | PMP, Reviewed-PDM | Product Tile - PMP/SRP | UI | No | Yes | Functional
Story | Shubhendu Singh | KOSPS-323 | Group Price - PMP/Search Page | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-28 08:14 | 2017-03-02 13:59 |  | 2017-03-13 | 0 | 13 | PMP, Reviewed-PDM | Product Tile - PMP/SRP | UI | No | Yes | Functional
Story | Shubhendu Singh | KOSPS-325 | Tiered Price - PMP/Search Page | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-29 00:16 | 2017-03-02 13:52 |  | 2017-03-13 | 0 | 13 | PMP, Reviewed-PDM | Product Tile - PMP/SRP | UI | No | Yes | Functional
Story | Unassigned | KOSPS-326 | Shipping Surcharge - PDP | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-29 00:58 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 13 | PDP, Reviewed-PDM | Product Tile | UI | No | Yes | Functional
Story | Unassigned | KOSPS-327 | Shipping Surcharge - Collection Page | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-29 01:06 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | Reviewed-PDM, collection_page | Collections Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-328 | Preview Pricing - Collection Page | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-29 01:27 | 2017-03-06 19:01 |  | 2017-03-13 | 0 | 2 | Reviewed-PDM, collection_page | Collections Page | UI | No | Yes | Functional
Story | Udeyandra Kumar | KOSPS-329 | Preview Pricing - PMP/Search Page | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-29 01:59 | 2017-03-02 13:54 |  | 2017-03-13 | 0 | 8 | PMP, Reviewed-PDM | Product Tile - PMP/SRP | UI | No | Yes | Functional
Story | Unassigned | KOSPS-334 | Guided Navigation - PMP/Search Page | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-29 05:27 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PMP, Reviewed-PDM | Generic Features - PMP/SRP | UI | No | Yes | Functional
Story | Nagamohan Gollapothu | KOSPS-335 | Batch Job – MDM Feed: Incremental catalog feed to new datastore - Phase 2 | Guru Gautam Rao | Medium | Done | Fixed | 2016-12-29 06:11 | 2017-03-05 21:39 | 2017-02-13 | 2017-03-13 | 1 | 18 | ATG_Changes, Reviewed-Team | Catalog Feed | Batch, Technical Backend | No | No | Technical
Story | Karandeep Singh | KOSPS-350 | Sort By - PMP/Search Page | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-29 06:42 | 2017-03-02 15:23 | 2017-02-22 | 2017-03-13 | 0 | 21 | PMP, Reviewed-PDM | PMP - Static Initial Page | UI | No | Yes | Functional
Story | Parthiban Natarajan | KOSPS-377 | Product Badges - PMP/Search Pages | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-29 10:44 | 2017-03-02 15:25 | 2017-02-23 | 2017-03-13 | 0 | 21 | PMP, Reviewed-PDM | PMP - Static Initial Page | UI | No | Yes | Functional
Story | Karandeep Singh | KOSPS-383 | Pagination & Products Per Page - PMP/Search Pages | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-30 02:03 | 2017-03-02 15:25 | 2017-02-23 | 2017-03-13 | 0 | 21 | PMP, Reviewed-PDM | PMP - Static Initial Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-386 | Navigation Links - PMP/Search Page | Aruna X Sharma | Medium | To Do | Unresolved | 2016-12-30 03:26 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 3 | PMP, Reviewed-PDM | Generic Features - PMP/SRP | UI | No | Yes | Functional
Story | Karandeep Singh | KOSPS-387 | BOPUS filter - PMP/Search Page | Aruna X Sharma | Medium | In Progress | Unresolved | 2016-12-30 05:13 | 2017-03-02 15:25 | 2017-02-23 | 2017-03-13 | 0 | 21 | PMP, Reviewed-PDM | PMP - Static Initial Page | UI | No | Yes | Functional
Story | Ramachandra Penukonda | KOSPS-389 | Process to flush akamai and apigee cache - Phase 2 | Guru Gautam Rao | Medium | In Progress | Unresolved | 2016-12-30 08:12 | 2017-03-01 09:35 | 2017-02-13 | 2017-03-13 | 0 | 18 |  |  |  | Yes | No | Technical
Story | Parthiban Natarajan | KOSPS-399 | Product Not Available Page | Aruna X Sharma | Medium | To Do | Unresolved | 2017-01-03 01:08 | 2017-03-03 12:46 |  | 2017-03-13 | 0 | 21 | PMP, Reviewed-PDM | Generic Features - PMP/SRP | UI | No | Yes | Functional
Story | Parthiban Natarajan | KOSPS-401 | No Search Result Page | Aruna X Sharma | Medium | In Progress | Unresolved | 2017-01-03 03:54 | 2017-03-03 12:42 |  | 2017-03-13 | 0 | 18 | PMP, Reviewed-PDM | Generic Features - PMP/SRP | UI | No | Yes | Functional
Story | Parthiban Natarajan | KOSPS-403 | Search Result Page messages | Aruna X Sharma | Medium | In Progress | Unresolved | 2017-01-03 05:02 | 2017-03-03 12:44 |  | 2017-03-13 | 0 | 18 | PMP, Reviewed-PDM | Generic Features - PMP/SRP | UI | No | Yes | Functional
Story | Amit Kumar Panda | KOSPS-406 | Back to Top - PMP/Search Pages | Aruna X Sharma | Medium | Done | Fixed | 2017-01-04 04:13 | 2017-03-02 15:30 | 2017-02-22 | 2017-03-13 | 1 | 8 | PMP, Reviewed-PDM | PMP - Static Initial Page | UI | No | Yes | Functional
Story | SaddikutiSreenivasa Reddy | KOSPS-426 | Convert Akamai Purge scheduler to batch job process | Guru Gautam Rao | Medium | In Progress | Unresolved | 2017-01-06 04:37 | 2017-03-01 09:36 | 2017-02-13 | 2017-03-13 | 0 | 13 |  | SnB Batch Jobs |  | No | No | Technical
Story | Unassigned | KOSPS-444 | keyword Search - Catalog API | Srinivas Meenavalli | Medium | Done | Fixed | 2017-01-09 05:26 | 2017-03-08 09:22 |  | 2017-03-13 | 1 | 2 |  | Catalog API |  | Yes | Yes | Technical
Story | Unassigned | KOSPS-445 | Dimension/Pagination Navigation - PMP | Srinivas Meenavalli | Medium | Done | Fixed | 2017-01-09 05:39 | 2017-03-08 09:23 |  | 2017-03-13 | 1 | 2 |  | Catalog API |  | Yes | Yes | Technical
Story | Unassigned | KOSPS-446 | Product count API for Store availability facet | Srinivas Meenavalli | Medium | Done | Fixed | 2017-01-09 05:42 | 2017-03-08 09:28 |  | 2017-03-13 | 1 | 2 |  | Catalog API |  | Yes | Yes | Technical
Story | Unassigned | KOSPS-450 | Omniture Tracking- Zero Search Results with RR ad's and Bigdata Recommendations | Aruna X Sharma | Medium | To Do | Unresolved | 2017-01-09 06:01 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PMP, Reviewed-PDM | Omniture - PLP/Search Pages | UI | No | Yes | Functional
Story | Unassigned | KOSPS-480 | Omniture Requirements: PMP Default | Aruna X Sharma | Medium | To Do | Unresolved | 2017-01-09 06:20 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PMP, Reviewed-PDM | Omniture - PLP/Search Pages | UI | No | Yes | Functional
Story | Unassigned | KOSPS-481 | Sale Event - Catalog API Service ( Open API) | Srinivas Meenavalli | Medium | Done | Fixed | 2017-01-09 06:24 | 2017-03-08 09:24 |  | 2017-03-13 | 1 | 2 |  | Catalog API |  | Yes | Yes | Technical
Story | Unassigned | KOSPS-483 | Omniture Requirements: Internal Search | Aruna X Sharma | Medium | To Do | Unresolved | 2017-01-09 06:28 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PMP, Reviewed-PDM | Omniture - PLP/Search Pages | UI | No | Yes | Functional
Story | Unassigned | KOSPS-490 | Omniture Requirements: Redirected Search | Aruna X Sharma | Medium | To Do | Unresolved | 2017-01-09 06:38 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PMP, Reviewed-PDM | Omniture - PLP/Search Pages | UI | No | Yes | Functional
Story | Unassigned | KOSPS-491 | Omniture Requirements: PMP Manual Refinement | Aruna X Sharma | Medium | To Do | Unresolved | 2017-01-09 06:43 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PMP, Reviewed-PDM | Omniture - PLP/Search Pages | UI | No | Yes | Functional
Story | Unassigned | KOSPS-492 | Omniture Requirements: PMP Sort/Pagination/PPP | Aruna X Sharma | Medium | To Do | Unresolved | 2017-01-09 06:49 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PMP, Reviewed-PDM | Omniture - PLP/Search Pages | UI | No | Yes | Functional
Story | Unassigned | KOSPS-493 | Omniture Requirements: Default Breadcrumb Removal | Aruna X Sharma | Medium | To Do | Unresolved | 2017-01-09 07:00 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PMP, Reviewed-PDM | Omniture - PLP/Search Pages | UI | No | Yes | Functional
Story | Unassigned | KOSPS-497 | Omniture Requirements: Refinement Removal | Aruna X Sharma | Medium | To Do | Unresolved | 2017-01-09 07:05 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PMP, Reviewed-PDM | Omniture - PLP/Search Pages | UI | No | Yes | Functional
Story | Unassigned | KOSPS-499 | Shop My store Omniture Tracking | Aruna X Sharma | Medium | To Do | Unresolved | 2017-01-09 07:11 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PMP, Reviewed-PDM | Omniture - PLP/Search Pages | UI | No | Yes | Functional
Story | Unassigned | KOSPS-500 | Search UI: Recent Searches - Omniture Tracking | Aruna X Sharma | Medium | To Do | Unresolved | 2017-01-09 07:15 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PMP, Reviewed-PDM | Omniture - PLP/Search Pages | UI | No | Yes | Functional
Story | Unassigned | KOSPS-509 | TA Keywords: Updated Omniture Requirements for TA Category Modifier | Aruna X Sharma | Medium | To Do | Unresolved | 2017-01-09 07:23 | 2017-03-06 19:01 |  | 2017-03-13 | 0 | 2 | PMP, Reviewed-PDM | Omniture - PLP/Search Pages | UI | No | Yes | Functional
Story | Unassigned | KOSPS-511 | Visual Nav: Omniture - Retain PFM values after leaving the page and returning | Aruna X Sharma | Medium | To Do | Unresolved | 2017-01-09 07:30 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PMP, Reviewed-PDM | Omniture - PLP/Search Pages | UI | No | Yes | Functional
Story | Unassigned | KOSPS-512 | UI: Visual Nav: Omniture Tracking | Aruna X Sharma | Medium | To Do | Unresolved | 2017-01-09 07:42 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PMP, Reviewed-PDM | Omniture - PLP/Search Pages | UI | No | Yes | Functional
Story | Unassigned | KOSPS-513 | Omniture: Browser back button behavior on PDP & PMP/Search page (BOPUS) | Aruna X Sharma | Medium | To Do | Unresolved | 2017-01-09 07:46 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PMP, Reviewed-PDM | Omniture - PLP/Search Pages | UI | No | Yes | Functional
Story | Unassigned | KOSPS-514 | TA Keywords: Omniture for tracking Category Modifier | Aruna X Sharma | Medium | To Do | Unresolved | 2017-01-09 07:51 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PMP, Reviewed-PDM | Omniture - PLP/Search Pages | UI | No | Yes | Functional
Story | Unassigned | KOSPS-515 | Personalized Browse: Omniture PFM variable when breadcrumb is deleted | Aruna X Sharma | Medium | To Do | Unresolved | 2017-01-09 07:54 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 2 | PMP, Reviewed-PDM | Omniture - PLP/Search Pages | UI | No | Yes | Functional
Story | Unassigned | KOSPS-516 | Visual type-ahead service | Srinivas Meenavalli | Medium | Done | Fixed | 2017-01-09 07:59 | 2017-03-08 09:25 |  | 2017-03-13 | 1 | 2 |  | Catalog API |  | Yes | Yes | Technical
Story | Unassigned | KOSPS-532 | Top navigation links Service - Open API | Srinivas Meenavalli | Medium | Done | Fixed | 2017-01-09 08:21 | 2017-03-08 09:27 |  | 2017-03-13 | 1 | 3 |  | Catalog API |  | Yes | Yes | Technical
Story | Sudhir Ikke | KOSPS-562 | Product Badges - Collection Pages | Aruna X Sharma | Medium | In Progress | Unresolved | 2017-01-10 06:01 | 2017-03-02 15:18 | 2017-02-24 | 2017-03-13 | 0 | 21 | Collection, Reviewed-PDM | PDP Collection - Static Initial Page | UI | No | Yes | Functional
Story | Unassigned | KOSPS-563 | Product Overlay Badge - PDP Page | Aruna X Sharma | Medium | To Do | Unresolved | 2017-01-10 06:41 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 3 | PDP, Reviewed-PDM | Product Tile | UI | No | Yes | Functional
Story | Unassigned | KOSPS-621 | Omniture Tracking: Product Accordions | Aruna X Sharma | Medium | To Do | Unresolved | 2017-01-12 06:34 | 2017-03-06 19:00 |  | 2017-03-13 | 0 | 3 | PMP, Reviewed-PDM | Omniture_PDP | UI | No | Yes | Functional
Story | Jyoti Prakash | KOSPS-655 | Dev Automation - Product Service Contract | tkmahir | Medium | In Progress | Unresolved | 2017-01-16 16:50 | 2017-03-01 09:35 | 2017-02-15 | 2017-03-13 | 0 | 8 |  | Dev Automation | Automation | No | Yes | QCOE
Story | Unassigned | KOSPS-680 | Browse/PMP Service - Catalog API - Pagination, Products per page and Sorting | Srinivas Meenavalli | Medium | Done | Fixed | 2017-01-17 08:32 | 2017-03-08 09:30 |  | 2017-03-13 | 1 | 3 |  | Catalog API |  | Yes | Yes | Technical
Story | Unassigned | KOSPS-681 | Browse/PMP Service - Catalog API - Implementation of Multi select - Transformation to OAPI contract | Srinivas Meenavalli | Medium | Done | Fixed | 2017-01-17 08:37 | 2017-03-08 09:30 |  | 2017-03-13 | 1 | 3 |  | Catalog API |  | Yes | Yes | Technical
Story | Unassigned | KOSPS-682 | Browse/PMP Service - Catalog API - Implementation of Hystrix for Solr service | Srinivas Meenavalli | Medium | Done | Fixed | 2017-01-17 08:41 | 2017-03-08 09:30 |  | 2017-03-13 | 1 | 3 |  | Catalog API |  | Yes | Yes | Technical
Story | Unassigned | KOSPS-683 | Browse/PMP Service - Catalog API - Transformation of Search JSON object to OAPI XML contract | Srinivas Meenavalli | Medium | Done | Fixed | 2017-01-17 08:42 | 2017-03-08 09:31 |  | 2017-03-13 | 1 | 3 |  | Catalog API |  | Yes | Yes | Technical
Story | Unassigned | KOSPS-684 | Browse/PMP Service - Catalog API -Getting the price details and transforming the response | Srinivas Meenavalli | Medium | Done | Fixed | 2017-01-17 08:43 | 2017-03-08 09:31 |  | 2017-03-13 | 1 | 3 |  | Catalog API |  | Yes | Yes | Technical
Story | Unassigned | KOSPS-685 | Browse/PMP Service - Catalog API -Getting the Inventory details and transforming the response | Srinivas Meenavalli | Medium | Done | Fixed | 2017-01-17 08:44 | 2017-03-08 09:31 |  | 2017-03-13 | 1 | 3 |  | Catalog API |  | Yes | Yes | Technical
Story | SaddikutiSreenivasa Reddy | KOSPS-753 | Implement ¦ Store in-store Offers Cache in Redis | Guru Gautam Rao | Medium | In Progress | Unresolved | 2017-01-24 06:23 | 2017-03-06 21:52 |  | 2017-03-13 | 0 | 18 |  | Pre-populate price cache |  | No | Yes | Technical
Story | SaddikutiSreenivasa Reddy | KOSPS-761 | Implement - Batch Slave - Populate price cache (Product) - Ecomm | Guru Gautam Rao | Medium | In Progress | Unresolved | 2017-01-24 06:44 | 2017-03-01 09:36 |  | 2017-03-13 | 0 | 18 |  | Pre-populate price cache |  | No | No | Technical
Story | Arya Priyadarshi | KOSPS-834 | Exception Handling and Logging (recommendations) - base framework | Manan Shah | High | In Progress | Unresolved | 2017-01-26 13:45 | 2017-03-08 03:27 |  | 2017-03-13 | 0 | 8 |  | PE SnB |  | Yes | Yes | Functional
Story | Sandeep Sirsgi | KOSPS-933 | Demo of Batch Jobs in LLE | Kiran Prabhakar Amba | Medium | Done | Fixed | 2017-01-31 18:49 | 2017-03-01 17:52 | 2017-02-15 | 2017-03-13 | 1 | 2 |  | New Batch Implementation | Batch, Technical Backend | No | No | Technical
Story | Bibhuti Patel | KOSPS-977 | Shell script for batch jobs | Guru Gautam Rao | Medium | In Progress | Unresolved | 2017-02-02 05:38 | 2017-03-01 09:35 |  | 2017-03-13 | 0 | 5 |  | New Batch Implementation |  | No | No | Technical
Story | Geetanjali Mandarapu | KOSPS-983 | Externalize log configurations to Zookeeper | Guru Gautam Rao | Medium | In Progress | Unresolved | 2017-02-02 06:50 | 2017-03-06 01:19 |  | 2017-03-13 | 0 | 8 |  | Upgrading Log4j in KOS code base |  | No | No | Technical
Story | Deepthi Vouligonda | KOSPS-1574 | KOS:PERF ¦¦ Benchmark for ATG Oracle DB | Bharat Kumar | High | In Progress | Unresolved | 2017-02-02 12:42 | 2017-03-07 11:53 |  | 2017-03-13 | 0 | 5 | PERF-KOS, PERF-KOS-SNB |  | Performance | No | No | Performance
Story | Amit Kumar Panda | KOSPS-988 | UI: PDP page rendering with static PDP JSON | Tarun Agarwal | High | Done | Fixed | 2017-02-02 14:13 | 2017-03-02 15:09 | 2017-02-24 | 2017-03-13 | 1 | 5 | UI | PDP - Static Initial Page | UI | No | No | Functional
Story | Prabakaran Krishnan | KOSPS-991 | Product API¦ Move Suppressed Pricing Text into Price Object | Shree Ramalingam | Medium | In Progress | Unresolved | 2017-02-02 16:15 | 2017-03-02 10:20 |  | 2017-03-13 | 0 | 13 |  | Product API |  | Yes | Yes | Functional
Story | Srinivas Meenavalli | KOSPS-1011 | Price API Changes... | Suresh Medavaram | Medium | In Progress | Unresolved | 2017-02-05 23:11 | 2017-03-02 06:52 |  | 2017-03-13 | 0 | 13 |  | Price Service |  | No | No | Technical
Story | Arya Priyadarshi | KOSPS-1025 | Implement Cache using Redis Template | Prabakaran Krishnan | Medium | In Progress | Unresolved | 2017-02-07 08:48 | 2017-03-01 09:34 |  | 2017-03-13 | 0 | 5 |  | Product API | Service | No | No | Technical
Story | Muthukumar Ramachandran | KOSPS-1030 | Dev Automation - Scene7 alt image create/delete process | Muthukumar Ramachandran | Medium | Done | Fixed | 2017-02-07 12:55 | 2017-03-03 17:56 |  | 2017-03-13 | 1 | 13 |  | Dev Automation | Automation | No | Yes | QCOE
Story | Manjunatha Sannaveeragowda | KOSPS-1048 | Analysis and design of the Product service API for store number | Manjunatha Sannaveeragowda | Medium | Done | Fixed | 2017-02-08 09:14 | 2017-03-04 03:55 |  | 2017-03-13 | 1 | 5 |  | Product API - In Store Implementation |  | Yes | Yes | Technical
Story | Itagi Bharmappa | KOSPS-1049 | Implementation of Product Service API - Store number | Manjunatha Sannaveeragowda | Medium | To Do | Unresolved | 2017-02-08 09:17 | 2017-03-09 02:38 |  | 2017-03-13 | 0 | 21 |  | Product API - In Store Implementation |  | Yes | Yes | Technical
Story | Bhanu Moorthy Konidena | KOSPS-1050 | TVS Corp Integration | Manjunatha Sannaveeragowda | Medium | In Progress | Unresolved | 2017-02-08 09:19 | 2017-03-09 04:13 |  | 2017-03-13 | 0 | 13 |  | Product API - In Store Implementation |  | Yes | Yes | Technical
Story | Muthukumar Ramachandran | KOSPS-1054 | Dev Automation - Inventory Service | Muthukumar Ramachandran | Medium | To Do | Unresolved | 2017-02-08 12:55 | 2017-03-01 09:34 |  | 2017-03-13 | 0 | 8 |  |  | Automation | No | Yes | QCOE
Story | Jyoti Prakash | KOSPS-1055 | Dev Automation - catalog service | Muthukumar Ramachandran | Medium | To Do | Unresolved | 2017-02-08 13:22 | 2017-03-01 09:36 |  | 2017-03-13 | 0 | 13 |  |  | Automation | No | Yes | QCOE
Story | Vidhya Pillai | KOSPS-1428 | KOS:PERF ¦¦ Benchmark for Inventory Grid | Abhishek Sawant | Medium | Done | Fixed | 2017-02-08 13:23 | 2017-03-01 23:56 |  | 2017-03-13 | 1 | 5 | PERF-KOS | S&B Performance | Performance | No | No | Performance
Story | Javeed Shaik | KOSPS-1056 | Dev automation -MDM Feed: Incremental catalog feed to new datastore(Batch job) | Muthukumar Ramachandran | Medium | In Progress | Fixed | 2017-02-08 13:37 | 2017-03-08 01:36 |  | 2017-03-13 | 1 | 13 |  |  | Automation | No | No | QCOE
Story | Siva Nagaraju Repalli | KOSPS-1156 | Price API for stores ( use Corp TVS Service) | Srinivas Meenavalli | Medium | In Progress | Fixed | 2017-02-09 08:28 | 2017-03-09 04:12 |  | 2017-03-13 | 1 | 8 |  | Price Service |  | Yes | Yes | Technical
Story | MahammadGhouse Guduru | KOSPS-1158 | Pruge Service Changes | MahammadGhouse Guduru | Medium | To Do | Fixed | 2017-02-09 09:08 | 2017-03-01 09:36 |  | 2017-03-13 | 1 | 3 |  |  | Service | No | No | Technical
Story | Bhanu Moorthy Konidena | KOSPS-1159 | Collection Pricing API | Sanjay Kumar Reddy Bandi | Medium | In Progress | Fixed | 2017-02-09 09:16 | 2017-03-01 09:36 |  | 2017-03-13 | 1 | 13 |  |  |  | No | Yes | Technical
Story | Prabakaran Krishnan | KOSPS-1178 | Mock outbound Services | Prabakaran Krishnan | Medium | In Progress | Fixed | 2017-02-09 11:57 | 2017-03-01 09:34 |  | 2017-03-13 | 1 | 13 |  | SnB NFR |  | No | No | Technical
Story | Ramachandra Penukonda | KOSPS-1289 | Implement - Slave - Populate price cache (Collection) - Ecomm | MahammadGhouse Guduru | Medium | In Progress | Fixed | 2017-02-10 04:37 | 2017-03-02 10:31 |  | 2017-03-13 | 1 | 13 |  | Pre-populate price cache |  | No | Yes | Functional
Story | GuruVenkatesh Grandi | KOSPS-1299 | Document StagingPreview Instance Configurations | Manjunatha Sannaveeragowda | Medium | Done | Fixed | 2017-02-10 05:12 | 2017-03-03 05:45 |  | 2017-03-13 | 1 | 2 |  | StagePreview-Services |  | No | No | Technical
Story | Geetanjali Mandarapu | KOSPS-1336 | HTTP Health and Readiness checks for SnB | Kirill Evstigneev | Medium | In Progress | Unresolved | 2017-02-10 09:35 | 2017-03-07 13:07 |  | 2017-03-13 | 0 | 13 |  |  |  | Yes | Yes | Functional
Story | Srinivasa Jayaraju | KOSPS-1337 | Incremental Feed - Kafka listener implementation | Guru Gautam Rao | Medium | In Progress | Unresolved | 2017-02-10 09:43 | 2017-03-06 14:27 |  | 2017-03-13 | 0 | 18 |  | Catalog Feed | Technical Backend | Yes | Yes | Technical
Story | Guru Gautam Rao | KOSPS-1347 | Batch job - MDM Feed : Handle deleted assets | Guru Gautam Rao | Medium | In Progress | Unresolved | 2017-02-10 13:18 | 2017-03-01 23:54 |  | 2017-03-13 | 0 | 8 |  | Catalog Feed | Technical Backend | No | Yes | Technical
Story | Deepthi Vouligonda | KOSPS-1366 | KOS:PERF ¦¦ WCS Performance Testing Strategy | Deepthi Vouligonda | Medium | In Progress | Unresolved | 2017-02-13 13:12 | 2017-03-07 11:20 |  | 2017-03-13 | 0 | 8 | PERF-KOS, PERF-KOS-SNB | S&B Performance | Performance | No | No | Performance
Story | Prabakaran Krishnan | KOSPS-1368 | PDP ¦ Do not show Promotion when product has Suppressed Pricing | Shree Ramalingam | Medium | In Progress | Unresolved | 2017-02-13 23:03 | 2017-03-09 11:44 |  | 2017-03-13 | 0 | 5 |  | Product API |  | Yes | Yes | Functional
Story | Prabakaran Krishnan | KOSPS-1370 | PDP ¦ Sale Price Compliance Updates | Shree Ramalingam | Medium | To Do | Unresolved | 2017-02-13 23:07 | 2017-03-08 13:31 |  | 2017-03-13 | 0 | 8 |  | Product API |  | Yes | Yes | Functional
Story | Jyoti Prakash | KOSPS-1388 | Static Key Service Automation deliverables | Ramkumar Kethepalli | Medium | To Do | Unresolved | 2017-02-14 21:29 | 2017-03-01 09:35 | 2017-02-23 | 2017-03-13 | 0 | 5 |  |  | Automation | No | Yes | Functional
Story | Udeyandra Kumar | KOSPS-1401 | PWP/GWP Offer display - PMP/Search Page | Aruna X Sharma | Medium | In Progress | Unresolved | 2017-02-15 01:01 | 2017-03-02 13:55 |  | 2017-03-13 | 0 | 18 | PMP, Reviewed-PDM | Product Tile - PMP/SRP | UI | No | Yes | Functional
Story | Udeyandra Kumar | KOSPS-1402 | GWP/PWP GET product on PMP/Search when qualified but not added to cart | Aruna X Sharma | Medium | In Progress | Unresolved | 2017-02-15 01:39 | 2017-03-02 13:58 |  | 2017-03-13 | 0 | 18 | PMP, Reviewed-PDM | Product Tile - PMP/SRP | UI | No | Yes | Functional
Story | Santosh Anupindi | KOSPS-1430 | PriceIntegration for Catalog | Santosh Anupindi | Medium | To Do | Unresolved | 2017-02-15 13:36 | 2017-03-01 09:37 |  | 2017-03-13 | 0 | 13 | Reviewed-Team | Catalog API | Service, Technical Backend | Yes | No | Functional
Story | Santosh Anupindi | KOSPS-1432 | KOS:PERF ¦¦ Capture Profiling Details for new S&B services | Yasmeen Akhtar | Medium | In Progress | Unresolved | 2017-02-15 17:05 | 2017-03-06 18:39 |  | 2017-03-13 | 0 | 5 | PERF-KOS | S&B Performance | Performance | No | No | Technical
Story | Javeed Shaik | KOSPS-1435 | Dev Automation - Data Load - One Time Load: Manual Test Cases Completion | Ramkumar Kethepalli | Medium | To Do | Unresolved | 2017-02-15 22:05 | 2017-03-01 09:35 |  | 2017-03-13 | 0 | 13 |  | Data Load - One time data load to be tested (Full Load) | Automation | No | Yes | Functional
Story | Jyoti Prakash | KOSPS-1437 | Dev Automation - Analysis & Manual test creation | Jyoti Prakash | Medium | Done | Fixed | 2017-02-15 23:48 | 2017-03-02 08:03 |  | 2017-03-13 | 1 | 5 |  | Dev Automation - Inventory Service | Automation | No | Yes | Functional
Story | Jyoti Prakash | KOSPS-1438 | Dev Automation - Automation Completion Inventory Service | Jyoti Prakash | Medium | In Progress | Unresolved | 2017-02-15 23:49 | 2017-03-01 09:34 |  | 2017-03-13 | 0 | 5 |  | Dev Automation - Inventory Service | Automation | No | Yes | Functional
Story | Raghavendra Dronamraju | KOSPS-1453 | Dev Automation - v1/catalog - Manual Test Creation | Jyoti Prakash | Medium | In Progress | Unresolved | 2017-02-16 06:20 | 2017-03-01 09:36 |  | 2017-03-13 | 0 | 2 |  | Catalog Service Automation | Automation | No | Yes | QCOE
Story | Raghavendra Dronamraju | KOSPS-1465 | Dev Automation - v1/catalog/category -Manual test creation | Jyoti Prakash | Medium | To Do | Unresolved | 2017-02-16 06:29 | 2017-03-01 14:53 |  | 2017-03-13 | 0 | 2 |  | Catalog Service Automation | Automation | No | Yes | QCOE
Story | Muthukumar Ramachandran | KOSPS-1471 | Dev Automation - ESK389 | Javeed Shaik | Medium | In Progress | Unresolved | 2017-02-16 06:31 | 2017-03-01 09:35 |  | 2017-03-13 | 0 | 5 |  | Dev Automation | Automation | No | Yes | Functional
Story | Muthukumar Ramachandran | KOSPS-1485 | Dev Automation - ESK389 - MDM Feed: Test Cases Automation Completion | Javeed Shaik | Medium | In Progress | Unresolved | 2017-02-16 07:17 | 2017-03-01 01:00 |  | 2017-03-13 | 0 | 5 |  | Batch job - MDM Feed : Handle deleted assets |  | No | Yes | QCOE
Story | Muthukumar Ramachandran | KOSPS-1483 | Dev Automation - ESK389 - MDM Feed: Manual Test Cases Completion | Javeed Shaik | Medium | Done | Fixed | 2017-02-16 07:17 | 2017-03-03 17:29 |  | 2017-03-13 | 1 | 5 |  | Batch job - MDM Feed : Handle deleted assets | Automation | No | No | QCOE
Story | KavitaAbhijeet Kulkarni | KOSPS-1488 | Dev Automation - ESK088 - Performics: Manual Test Cases Completion | Javeed Shaik | Medium | In Progress | Unresolved | 2017-02-16 07:23 | 2017-03-09 09:14 |  | 2017-03-13 | 0 | 3 |  | Batch - Epic to validate & Automate ESK 088 - Performics | Automation | No | Yes | QCOE
Story | Amit X Kumar | KOSPS-1512 | ESK600 code review | Muthukumar Ramachandran | Medium | Done | Fixed | 2017-02-16 14:45 | 2017-03-08 01:13 |  | 2017-03-13 | 1 | 2 |  | Dev Automation | Automation | No | No | Functional
Story | Veera Reddy Bommareddy | KOSPS-1514 | Login Page Implementation with LDAP authentication | Manan Shah | Medium | In Progress | Unresolved | 2017-02-16 16:39 | 2017-03-01 14:07 |  | 2017-03-13 | 0 | 8 |  | PE Dashboard |  | No | Yes | Functional
Story | Amit Kumar Panda | KOSPS-1520 | KOS: QA Story List | Srujana Seelam | Medium | To Do | Unresolved | 2017-02-16 17:58 | 2017-03-01 09:34 |  | 2017-03-13 | 0 | 3 |  |  |  | No | Yes | Functional
Story | KavitaAbhijeet Kulkarni | KOSPS-1530 | Dev Automation - ESK088 - Performics: Test Cases Automation Completion | Javeed Shaik | Medium | In Progress | Unresolved | 2017-02-17 04:38 | 2017-03-09 09:15 |  | 2017-03-13 | 0 | 18 |  | Batch - Epic to validate & Automate ESK 088 - Performics | Automation | No | Yes | QCOE
Story | KavitaAbhijeet Kulkarni | KOSPS-1532 | Dev Automation - ESK088 - Performics: Automation Execution completion (Env: Local / LLE) | Javeed Shaik | Medium | To Do | Unresolved | 2017-02-17 04:42 | 2017-03-01 18:51 |  | 2017-03-13 | 0 | 5 |  | Batch - Epic to validate & Automate ESK 088 - Performics | Automation | No | Yes | QCOE
Story | KavitaAbhijeet Kulkarni | KOSPS-1533 | Dev Automation - ESK088 - Performics: Verify and Close all outstanding issues | Javeed Shaik | Medium | To Do | Unresolved | 2017-02-17 04:43 | 2017-03-01 18:51 |  | 2017-03-13 | 0 | 2 |  | Batch - Epic to validate & Automate ESK 088 - Performics | Automation | No | Yes | QCOE
Story | Manjunatha Sannaveeragowda | KOSPS-1539 | Updating the module structure of Product and Price service | Manjunatha Sannaveeragowda | Medium | In Progress | Unresolved | 2017-02-17 05:49 | 2017-03-03 06:16 |  | 2017-03-13 | 0 | 8 |  | Product API | Service | No | No | Technical
Story | Jyoti Prakash | KOSPS-1545 | Dev Automation - v1/catalog - Automation Completion | Raghavendra Dronamraju | Medium | In Progress | Unresolved | 2017-02-17 06:17 | 2017-03-01 09:35 |  | 2017-03-13 | 0 | 8 |  | Catalog Service Automation | Automation | No | Yes | Functional
Story | Jyoti Prakash | KOSPS-1546 | Dev Automation - v1/catalog - Automation Execution | Raghavendra Dronamraju | Medium | In Progress | Unresolved | 2017-02-17 06:19 | 2017-03-01 09:35 |  | 2017-03-13 | 0 | 2 |  | Catalog Service Automation | Automation | No | No | Functional
Story | Jyoti Prakash | KOSPS-1547 | Dev Automation - v1/catalog - Close All OutStanding Issues | Raghavendra Dronamraju | Medium | To Do | Unresolved | 2017-02-17 06:21 | 2017-03-01 18:52 |  | 2017-03-13 | 0 | 2 |  | Catalog Service Automation | Automation | No | Yes | Functional
Story | Raghavendra Dronamraju | KOSPS-1548 | Dev Automation - v1/catalog/{dimensionValueID} - Manual Test Creation | Raghavendra Dronamraju | Medium | To Do | Unresolved | 2017-02-17 06:26 | 2017-03-01 14:52 |  | 2017-03-13 | 0 | 8 |  | Catalog Service Automation | Automation | No | Yes | Functional
Story | Raghavendra Dronamraju | KOSPS-1549 | Dev Automation - v1/catalog/{dimensionValueID} - Automation completion | Raghavendra Dronamraju | Medium | To Do | Unresolved | 2017-02-17 06:27 | 2017-03-01 14:53 |  | 2017-03-13 | 0 | 8 |  | Catalog Service Automation | Automation | No | Yes | Functional
Story | Raghavendra Dronamraju | KOSPS-1550 | Dev Automation - v1/catalog/{dimensionValueID} - Automation Execution | Raghavendra Dronamraju | Medium | To Do | Unresolved | 2017-02-17 06:28 | 2017-03-01 14:53 |  | 2017-03-13 | 0 | 2 |  | Catalog Service Automation | Automation | No | Yes | Functional
Story | Raghavendra Dronamraju | KOSPS-1551 | Dev Automation - v1/catalog/{dimensionValueID} - Close All OutStanding Issues | Raghavendra Dronamraju | Medium | To Do | Unresolved | 2017-02-17 06:30 | 2017-03-01 14:53 |  | 2017-03-13 | 0 | 2 |  | Catalog Service Automation | Automation | No | Yes | Functional
Story | Jyoti Prakash | KOSPS-1552 | Dev Automation - v1/catalog/category -Automation Completion | Raghavendra Dronamraju | Medium | To Do | Unresolved | 2017-02-17 06:35 | 2017-03-01 14:55 |  | 2017-03-13 | 0 | 8 |  | Catalog Service Automation | Automation | No | Yes | Functional
Story | Jyoti Prakash | KOSPS-1553 | Dev Automation - v1/catalog/category -Automation Execution | Raghavendra Dronamraju | Medium | To Do | Unresolved | 2017-02-17 06:36 | 2017-03-01 14:54 |  | 2017-03-13 | 0 | 2 |  | Catalog Service Automation | Automation | No | Yes | Functional
Story | Jyoti Prakash | KOSPS-1554 | Dev Automation - v1/catalog/category -Close All OutStanding Issues | Raghavendra Dronamraju | Medium | To Do | Unresolved | 2017-02-17 06:38 | 2017-03-01 14:54 |  | 2017-03-13 | 0 | 2 |  | Catalog Service Automation | Automation | No | Yes | Functional
Story | Manmeet Singh | KOSPS-1573 | KOS:PERF ¦¦ Mongo DB-Create a Script and Scenario To Execute DB Queries on Mongo DB | Mohan Tanguturi | Medium | In Progress | Unresolved | 2017-02-17 19:10 | 2017-03-08 13:29 |  | 2017-03-13 | 0 | 5 | PERF-KOS, PERF-KOS-SNB |  | Performance | Yes | Yes | Performance
Story | Sivaram Rajanala | KOSPS-1588 | Cloudops : Provide all the requirements and setup instructions for KASS, Hystrix tools | Sivaram Rajanala | Critical | In Progress | Unresolved | 2017-02-19 15:50 | 2017-03-02 14:21 |  | 2017-03-13 | 0 | 18 |  | PE Dashboard |  | No | No | Functional
Story | Ananda Vangara | KOSPS-1597 | Product Lookup with MongoDB | Ritwik Veeresh Anburmath | High | In Progress | Unresolved | 2017-02-20 13:54 | 2017-03-02 09:48 |  | 2017-03-13 | 0 | 18 |  | PE Dashboard |  | Yes | Yes | Functional
Story | Jyoti Prakash | KOSPS-1614 | Dev Automation - Automation Execution for Inventory service | Jyoti Prakash | Medium | In Progress | Unresolved | 2017-02-21 07:13 | 2017-03-01 09:35 |  | 2017-03-13 | 0 | 2 |  | Dev Automation - Inventory Service | Automation | No | Yes | Functional
Story | Raghavendra Dronamraju | KOSPS-1613 | Dev Automation - Manual Test Creation | Raghavendra Dronamraju | Medium | Done | Fixed | 2017-02-21 07:13 | 2017-03-02 08:05 |  | 2017-03-13 | 1 | 5 |  | Dev Automation - Static Content Service | Automation | No | Yes | Functional
Story | Jyoti Prakash | KOSPS-1616 | Dev Automation - Close All OutStanding Issues - Inventory service | Jyoti Prakash | Medium | In Progress | Unresolved | 2017-02-21 07:17 | 2017-03-07 07:53 |  | 2017-03-13 | 0 | 2 |  | Dev Automation - Inventory Service |  | No | Yes | Functional
Story | Raghavendra Dronamraju | KOSPS-1617 | Dev Automation - Automation Completion Static Content Services | Raghavendra Dronamraju | Medium | Done | Fixed | 2017-02-21 07:19 | 2017-03-02 08:06 |  | 2017-03-13 | 1 | 8 |  | Dev Automation - Static Content Service | Automation | No | Yes | Functional
Story | Jyoti Prakash | KOSPS-1618 | Dev Automation - Automation Execution Static Content Services | Raghavendra Dronamraju | Medium | Done | Fixed | 2017-02-21 07:22 | 2017-03-02 23:32 |  | 2017-03-13 | 1 | 2 |  | Dev Automation - Static Content Service | Automation | No | Yes | Functional
Story | Raghavendra Dronamraju | KOSPS-1619 | Dev Automation - Close All OutStanding Issues - Static Content Services | Raghavendra Dronamraju | Medium | Done | Fixed | 2017-02-21 07:23 | 2017-03-02 23:32 |  | 2017-03-13 | 1 | 2 |  | Dev Automation - Static Content Service |  | No | Yes | Functional
Story | KavitaAbhijeet Kulkarni | KOSPS-1635 | Dev Automation - BCC Publishing : Manual Test Cases Completion | Javeed Shaik | Medium | Done | Fixed | 2017-02-22 06:50 | 2017-03-09 02:52 |  | 2017-03-13 | 1 | 5 | Automation | Dev Automation - Catalog Feed |  | No | Yes | QCOE
Story | KavitaAbhijeet Kulkarni | KOSPS-1639 | Dev Automation - BCC Publishing - Manual Execution completion (Env: Local / LLE) | Javeed Shaik | Medium | In Progress | Unresolved | 2017-02-22 07:18 | 2017-03-09 02:57 |  | 2017-03-13 | 0 | 13 | Automation | Dev Automation - Catalog Feed |  | No | Yes | QCOE
Story | KavitaAbhijeet Kulkarni | KOSPS-1640 | Dev Automation - BCC Publishing - Verify and Close all outstanding issues | Javeed Shaik | Medium | In Progress | Unresolved | 2017-02-22 07:27 | 2017-03-09 03:06 |  | 2017-03-13 | 0 | 2 | Automation | Dev Automation - Catalog Feed |  | No | Yes | QCOE
Story | KavitaAbhijeet Kulkarni | KOSPS-1642 | Dev Automation - ESK613 Price: Manual Test Cases Completion | KavitaAbhijeet Kulkarni | Medium | Done | Fixed | 2017-02-22 07:40 | 2017-03-07 12:30 |  | 2017-03-13 | 1 | 8 |  | Dev Automation - ESK613 Price Cache Pre-populate Batch Job | Automation | No | Yes | QCOE
Story | KavitaAbhijeet Kulkarni | KOSPS-1643 | Dev Automation - ESK613 Price: Test Cases Automation Completion | KavitaAbhijeet Kulkarni | Medium | In Progress | Unresolved | 2017-02-22 07:41 | 2017-03-01 09:35 |  | 2017-03-13 | 0 | 8 |  | Dev Automation - ESK613 Price Cache Pre-populate Batch Job | Automation | No | Yes | QCOE
Story | KavitaAbhijeet Kulkarni | KOSPS-1645 | Dev Automation - ESK613 Price: Verify and Close all outstanding issues | KavitaAbhijeet Kulkarni | Medium | To Do | Unresolved | 2017-02-22 07:42 | 2017-03-01 18:50 |  | 2017-03-13 | 0 | 2 |  | Dev Automation - ESK613 Price Cache Pre-populate Batch Job | Automation | No | Yes | QCOE
Story | KavitaAbhijeet Kulkarni | KOSPS-1644 | Dev Automation - ESK613 Price: Automation Execution completion (Env: Local / LLE) | KavitaAbhijeet Kulkarni | Medium | To Do | Unresolved | 2017-02-22 07:42 | 2017-03-01 18:50 |  | 2017-03-13 | 0 | 5 |  | Dev Automation - ESK613 Price Cache Pre-populate Batch Job | Automation | No | Yes | QCOE
Story | Guru Gautam Rao | KOSPS-1652 | Add new fields in product service response | Shree Ramalingam | Medium | In Progress | Unresolved | 2017-02-22 13:19 | 2017-03-08 01:48 |  | 2017-03-13 | 0 | 5 |  | Product API |  | Yes | Yes | Functional
Story | Haroon Dogar | KOSPS-1660 | Collections - Static Page | Haroon Dogar | Medium | Done | Fixed | 2017-02-23 16:11 | 2017-03-06 14:18 |  | 2017-03-13 | 1 | 5 |  |  |  | No | Yes | Functional
Story | Haroon Dogar | KOSPS-1659 | PDP - Static Page | Haroon Dogar | Medium | Done | Fixed | 2017-02-23 16:11 | 2017-03-06 14:19 |  | 2017-03-13 | 1 | 5 |  |  |  | No | Yes | Functional
Story | Haroon Dogar | KOSPS-1661 | PMP - Static Page | Haroon Dogar | Medium | Done | Fixed | 2017-02-23 16:14 | 2017-03-06 14:18 |  | 2017-03-13 | 1 | 5 |  |  |  | No | Yes | Functional
Story | SaddikutiSreenivasa Reddy | KOSPS-1675 | Expose REST url for killing batch job | Guru Gautam Rao | Medium | In Progress | Unresolved | 2017-02-24 14:34 | 2017-03-02 11:19 |  | 2017-03-13 | 0 | 2 |  | SnB Batch Jobs | Service | No | No | Technical
Story | Narayana Jampani | KOSPS-1676 | Price Service implementation changes for using TVS integration | Guru Gautam Rao | Medium | In Progress | Unresolved | 2017-02-24 14:37 | 2017-03-02 11:19 |  | 2017-03-13 | 0 | 8 |  | Price Service | Service | No | No | Technical
Story | MahammadGhouse Guduru | KOSPS-1677 | Analysis ¦ Using Kafka with compression | Guru Gautam Rao | Medium | In Progress | Unresolved | 2017-02-24 14:41 | 2017-03-03 06:26 |  | 2017-03-13 | 0 | 8 |  | SnB Batch Jobs |  | Yes | Yes | Technical
Story | Rohit Kumar | KOSPS-1680 | KOS:PERF ¦¦ Recording SNB Scripts In SNBPERF01 Environment | Yasmeen Akhtar | Medium | In Progress | Unresolved | 2017-02-25 00:31 | 2017-03-08 13:28 |  | 2017-03-13 | 0 | 5 | PERF-KOS, PERF-KOS-SNB |  |  | Yes | No | Performance
Story | Guru Gautam Rao | KOSPS-1714 | Get Category Master from Mongo | Guru Gautam Rao | Medium | In Progress | Unresolved | 2017-02-26 04:11 | 2017-03-07 05:42 |  | 2017-03-13 | 0 | 13 |  |  |  | No | Yes | Technical
Story | Guru Gautam Rao | KOSPS-1758 | Update the Created and updated date in Mongo DB | Guru Gautam Rao | Medium | In Progress | Unresolved | 2017-02-26 11:53 | 2017-03-07 03:32 |  | 2017-03-13 | 0 | 5 |  | Catalog Feed |  | No | Yes | Technical
Story | Manjunatha Sannaveeragowda | KOSPS-1769 | Zookeeper changes in product and price services | Manjunatha Sannaveeragowda | Medium | In Progress | Unresolved | 2017-02-27 08:47 | 2017-03-02 11:18 |  | 2017-03-13 | 0 | 8 |  |  | Service | No | Yes | Technical
Story | Raghavendra Dronamraju | KOSPS-1776 | Dev Automation - v1/Catalog/Propensity - Manual Test Creation | Raghavendra Dronamraju | Medium | In Progress | Unresolved | 2017-02-28 01:49 | 2017-03-06 06:32 |  | 2017-03-13 | 0 | 2 |  | Catalog Service Automation |  | No | Yes | Functional
Story | Raghavendra Dronamraju | KOSPS-1777 | Dev Automation - v1/Catalog/Propensity - Automation Completion | Raghavendra Dronamraju | Medium | In Progress | Unresolved | 2017-02-28 01:51 | 2017-03-07 07:59 |  | 2017-03-13 | 0 | 8 |  | Catalog Service Automation |  | No | Yes | Functional
Story | Raghavendra Dronamraju | KOSPS-1782 | Dev Automation - v1/Catalog/Visual Type Ahead - Manual Test Creation | Raghavendra Dronamraju | Medium | In Progress | Unresolved | 2017-02-28 02:07 | 2017-03-06 06:32 |  | 2017-03-13 | 0 | 2 |  | Catalog Service Automation |  | No | Yes | Functional
Story | Raghavendra Dronamraju | KOSPS-1783 | Dev Automation - v1/Catalog/Visual Type Ahead - Automation Completion | Raghavendra Dronamraju | Medium | In Progress | Unresolved | 2017-02-28 02:09 | 2017-03-14 |  | 2017-03-27 | 0 | 8 |  | Catalog Service Automation |  | No | Yes | Functional
Story | Raghavendra Dronamraju | KOSPS-1784 | Dev Automation - v1/Catalog/Visual Type Ahead - Automation Execution | Raghavendra Dronamraju | Medium | In Progress | Unresolved | 2017-02-28 02:10 | 2017-03-14 |  | 2017-03-27 | 0 | 2 |  | Catalog Service Automation |  | No | Yes | Functional
Story | Javeed Shaik | KOSPS-1804 | Dev Automation - Implement 494/495 new changes | Muthukumar Ramachandran | Medium | In Progress | Unresolved | 2017-03-01 00:44 | 2017-03-14 |  | 2017-03-27 | 0 | 5 |  |  | Automation | No | No | Functional
Story | Aravinth Chandrasekaran | KOSPS-1805 | Move the batch job from ActiveMQ to Kafka | Aravinth Chandrasekaran | Medium | Done | Fixed | 2017-03-01 01:24 | 2017-03-06 12:10 |  | 2017-03-13 | 1 | 5 |  | Catalog Feed |  | No | No | Technical
Story | Sandeep Sirsgi | KOSPS-1806 | ESK473 : Implementation | Sandeep Sirsgi | Medium | In Progress | Unresolved | 2017-03-01 15:39 | 2017-03-01 18:53 |  | 2017-03-13 | 0 | 21 | Batch | SnB Batch Jobs | Batch | Yes | Yes | Functional
Story | Bibhuti Patel | KOSPS-1814 | All Batch - Refactoring folder structure (Google Storage Bucket and in Batch Master Servers) | Aravinth Chandrasekaran | Medium | In Progress | Unresolved | 2017-03-01 23:31 | 2017-03-09 09:46 |  | 2017-03-13 | 0 | 8 |  | SnB Batch Jobs | Batch | No | Yes | Technical
Story | Srinivas Meenavalli | KOSPS-1827 | Price API - StagingPreview implementation | Srinivas Meenavalli | Medium | In Progress | Unresolved | 2017-03-02 03:15 | 2017-03-03 05:46 |  | 2017-03-13 | 0 | 8 |  | StagePreview-Services | Service | Yes | Yes | Technical
Story | Siva Nagaraju Repalli | KOSPS-1829 | Product API - StagingPreview implementation | Srinivas Meenavalli | Medium | In Progress | Unresolved | 2017-03-02 03:25 | 2017-03-07 03:09 |  | 2017-03-13 | 0 | 5 |  | StagePreview-Services | Service | Yes | Yes | Technical
Story | MahammadGhouse Guduru | KOSPS-1845 | Implement suggestions from Redis Labs | Guru Gautam Rao | Medium | To Do | Unresolved | 2017-03-02 07:39 | 2017-03-02 11:18 |  | 2017-03-13 | 0 | 8 |  | SnB Batch Jobs | Service | Yes | No | Technical
Story | Yasmeen Akhtar | KOSPS-1849 | KOS:PERF ¦¦ Direct Component Testing ¦¦ NodeJS | Yasmeen Akhtar | Medium | In Progress | Unresolved | 2017-03-02 17:46 | 2017-03-06 18:44 |  | 2017-03-13 | 0 | 13 | PERF-KOS, PERF-KOS-SNB |  | Performance | Yes | No | Performance
Story | Aravinth Chandrasekaran | KOSPS-1855 | DataImportJob improvements | Aravinth Chandrasekaran | Medium | In Progress | Unresolved | 2017-03-03 12:03 | 2017-03-06 12:11 |  | 2017-03-13 | 0 | 8 |  | Catalog Feed |  | No | No | Performance
Story | Ankita Singh | KOSPS-1860 | KOS:PERF ¦¦ Direct test for REDIS | Vidhya Pillai | Medium | To Do | Unresolved | 2017-03-06 00:14 | 2017-03-06 18:48 |  | 2017-03-13 | 0 | 13 | PERF-KOS, PERF-KOS-SNB |  |  | Yes | No | Performance
Story | Shivendra Pratap Sing | KOSPS-1861 | KOS:PERF ¦¦ Direct Component Testing ¦¦ Catalog Service API | Yasmeen Akhtar | Medium | In Progress | Unresolved | 2017-03-06 00:15 | 2017-03-09 13:04 |  | 2017-03-13 | 0 | 13 | PERF-KOS, PERF-KOS-SNB |  |  | Yes | No | Performance
Story | Vidhya Pillai | KOSPS-1862 | KOS:PERF ¦¦ Direct test for KAFKA | Vidhya Pillai | Medium | To Do | Unresolved | 2017-03-06 00:19 | 2017-03-06 18:54 |  | 2017-03-13 | 0 | 13 | PERF-KOS, PERF-KOS-SNB |  |  | Yes | No | Performance
Story | Santosh Anupindi | KOSPS-1864 | KOS : PERF ¦¦ Redis Cache Details | Vidhya Pillai | Medium | To Do | Unresolved | 2017-03-06 17:03 | 2017-03-06 18:46 |  | 2017-03-13 | 0 | 2 | PERF-KOS, PERF-KOS-SNB |  |  | No | No | Technical
Story | Vidhya Pillai | KOSPS-1865 | KOS:PERF ¦¦ Direct Component Testing ¦¦ Product Service API | Yasmeen Akhtar | Medium | To Do | Unresolved | 2017-03-06 18:34 | 2017-03-06 18:45 |  | 2017-03-13 | 0 | 13 | PERF-KOS, PERF-KOS-SNB |  |  | Yes | Yes | Performance
Story | RiteshKumar Ketireddi | KOSPS-1866 | KOS:PERF ¦¦ Direct test for ESK389 | Yasmeen Akhtar | Medium | To Do | Unresolved | 2017-03-06 19:18 | 2017-03-06 19:19 |  | 2017-03-13 | 0 | 13 |  |  |  | Yes | No | Performance
Story | MahammadGhouse Guduru | KOSPS-1871 | Refactoring Repository Model & Implementation in SnB Batch | MahammadGhouse Guduru | Medium | In Progress | Unresolved | 2017-03-07 00:51 | 2017-03-08 08:09 |  | 2017-03-13 | 0 | 5 |  |  |  | No | No | Functional

## Sheet1
Sprint Start Date | SprintEndDate
2016-12-06 | 2016-12-19
2016-12-20 | 2017-01-02
2017-01-03 | 2017-01-16
2017-01-17 | 2017-01-30
2017-01-31 | 2017-02-13
2017-02-14 | 2017-02-27
2017-02-28 | 2017-03-13
2017-03-14 | 2017-03-27
Assumptions
All Requirements are entered in JIRA and captured in this spreadsheet
Update date is considered to be the latest updates on the requirement
All Sprints are two weeks effort
Sprint Dates table calendar above is computed from the earliest available Requirements Create date and the latest Update Date
Sprint calendar on the left is created from the earliest and latest dates to compute targetdate
Target Date Calculation
Check for the Update Date (Column J in worksheet geenral_report
Index / Match the date to the Sprint Calendar in Sheet1
Choose the Sprint End date to be the Target Date for the requirement (Story, Task, Bug or Epic)
Use the Resolution field to identify classification (Completed or not completed as 1 or 0
Added two columns L and M to indicate the Target Date and Classification
Note 1: I have modified some of the records Resolution to be "Fixed" so that we could get the necessary classification
Note 2: I have changed some of the updated date to pick the right sprint end date for the target date